## Test Report
UPTOWN IT - FUNCTIONALITY TEST REPORT for ICTWEB519/520 Assessment 2
High | Completed | Unit Testing
Medium | Failed | Integrated Testing
Low | In-progress | System Testing
| Not started | Acceptance Testing
PROJECT | TEST NO: | 1 | ATTENDEES | Programmer: | Mark Beresford | TEST TYPE | Select test type
| Project Ref.: | ICTWEB519/520 Assessment 2 |  | Project Manager: | Cameron Hughes |  | Acceptance Testing
| Client: | ABC Optical |  | Lead Tester: | Mark Beresford
| Date: | 2023-05-08 |  | Other:
Pre-conditions: | Single Page Website with links to each section
TESTS | TEST CASES | METHOD Select from List | EXPECTED RESULT | ACTUAL RESULT | PRIORITY Select from List | STATUS Select from List | COMMENTS
Client Requirements | Local Business | Acceptance Testing | "Local" keyword in title | "Local" keyword in title | High | Completed
| Young Families | Acceptance Testing | Image of child or young family, with "family" keyword in title | Image of child wearing glasses, and "families" keyword in title | High | Completed | Image of child chosen which matched the colour scheme
| Improve quality of life | Acceptance Testing | "quality of life" keywords in title | '"quality of life" keywords in title | High | Completed
Design Requirements | Sections
| Contact Form | Acceptance Testing | Form included | Form included | High | Completed
| List of services | Acceptance Testing | List of services included | List of services included | High | Completed
| Contact details | Acceptance Testing | Contact details | Contact details included in footer | High | Completed
| Operating Hours | Acceptance Testing | Operating hours included in footer | Operating hours | High | Completed
| About us | Acceptance Testing | About us section included | About us section included | High | Completed
Wireframe comparison | Desktop Layout Accuracy | Acceptance Testing | Desktop website follows Desktop wireframe | Desktop website follows Desktop wireframe | High | Completed
| Mobile Layout Accuracy | Acceptance Testing | Mobile devices follow Mobile wireframe | Majority of mobile devices follow Mobile wireframe | High | Completed | As most devices have different pixel width and height sizes, some images have been removed to fit content
| Responsive Accuracy | Acceptance Testing | Website maintains Desktop accuracy for lower pixel widths | Website maintains Desktop accuracy for lower pixel widths through breakpoints added | High | Completed | Breakpoints added at 1300px, 1000px, 810px, 585px, 400px and specific sizes for galaxy fold and iPhone SE
Styling Requirements | Colour Scheme:
| Background | Acceptance Testing | A shade of Green Background for Title, services and form background. All others plain white. | Header(inc title) and services uses gradient of lighter green to darker green.Form has a light green background. All others white(#fff) | High | Completed
| Buttons/Links | Acceptance Testing | Button/link backgrounds will all share the same green colour with box shadows. Text will be the cream. CTA buttons/links will use a paler red. | Button/link backgrounds are green with box shadows shown on hover. Text is cream. CTA buttons/links use a paler red. | High | Completed
| Palette | Acceptance Testing | A range from the colour palette to be used | Whole colour pallete used | High | Completed
| Icons | Acceptance Testing | Dark green icons, light green background if needed | Icons used in 2 sections, 1 section used light green background | Medium | Completed | light green background tested on list icons, but added no value
| Text | Acceptance Testing | Headings to use a darker shade of primary green colour. Text to use a lighter black for readibility | Headings use #0b240f(a very dark version of the primary green). Text uses #090909(a lighter black). | High | Completed
| White space | Acceptance Testing | Each section to use whole screen | Each section has height:100vh set | High | Completed
Forms:
| Background | Acceptance Testing | Light green background | Light green background used | High | Completed
| Label | Acceptance Testing | Capitalize. | Capitalized | Medium | Completed
| Input fields | Acceptance Testing | Green borders | Dark green borders used | Medium | Completed
| Submit button | Acceptance Testing | As cta button | Same As cta button, green with a hover red with scale | High | Completed
Font-sizes
| Heading 1 | Acceptance Testing | 54 pixels | 54 pixels | High | Completed
| Heading 2 | Acceptance Testing | 20 pixels | 20 pixels | High | Completed
| Heading 3 | Acceptance Testing | 24 pixels | 24 pixels | High | Completed
| Heading 4 | Acceptance Testing | 24 pixels | 24 pixels | High | Completed
| Links | Acceptance Testing | 18 pixels | 18 pixels | High | Completed
| Paragraphs | Acceptance Testing | 16 pixels | 16 pixels | High | Completed
| Fig Captions | Acceptance Testing | 16/14/12 pixels | Blockquote - 16 pixels. Name - 14 pixels. Job title - 12 pixels | High | Completed | Different sizes used for blockquote,name and position
| Unordered Lists | Acceptance Testing | 16 pixels | 16 pixels | High | Completed
| Labels | Acceptance Testing | 12 pixels | 12 pixels | High | Completed
| Inputs | Acceptance Testing | 16 pixels | 16 pixels | High | Completed
| Button text | Acceptance Testing | 16 pixels | 16 pixels | High | Completed
| Image sizes | Acceptance Testing | Small Images 300kb or less - Large Images 1mb or less | Largest Image - 856kb Small Images 200kb | High | Completed
Font-family
| Headings | Acceptance Testing | Lato | All headings in 'Lato' font | High | Completed
| All Text | Acceptance Testing | All text (inc form input) Montserrat | All text (inc form input) Montserrat | High | Completed
| Lists | Acceptance Testing | Montserrat | Montserrat | High | Completed
| Back-up | Acceptance Testing | sans serif | If primary fonts unavailable, sans serif is selected | High | Completed | tested by removing primary font in dev tools
Functional Requirements | Section links | Acceptance Testing | When links clicked, page should scroll to the link section | All links work as expected | High | Completed
| Section Display | Acceptance Testing | Each section should occupy 100% of the screen height | All sections occupy 100% of viewport height | High | Completed
| HTML Validation | Acceptance Testing | HTML should pass W3C validation with no errors | After 3 rounds of testing, the HTML passes W3C validation | High | Completed
| CSS Validation | Acceptance Testing | CSS should pass W3C validation with no errors | After 1 round of testing, the CSS passes W3C validation | High | Completed
| Accessibility Validation | Acceptance Testing | Website should comply with WCAG 2.0(Level AA) | After 2 rounds of testing, website passes WCAG 2.0(Level AA) | High | Completed | 75 potential problems remain
Browser Testing:
| Google Chrome | Acceptance Testing | Website to perform as expected in browser | Website performs as expected in browser | High | Completed | Browser looks as wireframe
| Opera | Acceptance Testing | Website to perform as expected in browser | Website performs as expected in browser | High | Completed | Browser looks as wireframe
Device Testing:
| Samsung Galaxy S20 Ultra | Acceptance Testing | Website to perform as expected on device | Website performs as expected on device | High | Completed | Device looks as wireframe
| iPhone 12 Pro | Acceptance Testing | Website to perform as expected on device | Website performs as expected on device | High | Completed | Device needed some images removed because of low pixel resolution
PROGRAMMER Signature: Date: 8/5/23 |  | PROJECT MANAGER Signature: Date: |  | LEAD TESTER Signature: Date: 8/5/23 |  | OTHER Signature: Date: